## Checklist - Checklist
Checklist
DONE | Date | Task |  |  |  | Asignee | STATUS | QA
FALSE | 1 | Notifikasi
FALSE | 1.a | Pesan error over limit => BIndo, refine |  | Notification Table | Menu admin setting/notif | Emulate on UMG for IB reject Message | SimasPay return RC13 (need to change to 63/ either by modify or masking by UMG)
FALSE | 1.b | Notif SMS topUp has to mention Amount popup => refine |  | ${Amount} |  | List Exported@Ary | Create update and insert Script
FALSE | 1.c | Notif Blokir/Upgrade akun => BIndo, refine |  | Notification Table
FALSE | 1.d | Some SMS/App message contains “simobi” => refine |  | Find Replace “Simobi” | Menu admin setting/notif | Martin
FALSE | 1.e | Add notif on blocking akan both by admin/3x wrong pwd => check and add new notif |  | ?? Java | Menu admin setting/notif | @Didik byadmin
FALSE
FALSE | 2 | History Transaction (Statement)
FALSE | 2.a | Menampilkan refId pada Statement (history) app. => FE only | FE |  |  | @Widy
FALSE | 2.b | Union with pending Trx => change SQL union 2 table=> BE Statement Service | BE - API | ??hibm criteria | Scheduler reversal | How to detect Scheduler is running
FALSE | 2.c | Reversal trx on stmt => check Stmt API |  | ??test | VA??
FALSE | 2.d | TopUp VA description => Refine generic terms (incoming top up) | BE | ?? | trxdesc, txn_tab.displayname
FALSE
FALSE | 3 | Show redeem info/procedure | FE |  |  | @Widy
FALSE
FALSE | 4 | Show Transaction Ref Num to be used on reconcile | Recon Procedure | Confirm refine
FALSE
FALSE | 5 | Dual Control for Parameter Changes => Procedure (SOP)
FALSE
TRUE | 6 | Remove Gopay/Gojek Driver menu | BE | BE to disabled Cofig.xml/json | Category | vi /opt/tomcat/mfino_conf/CategoryFiles/category.payment.txt |  | TESTED
FALSE
FALSE | 7 | MFINO Activity Log
FALSE | 7.a | Sort by Date asc, User Activity Log | BE- WEB | ?? | Sort asc | @kris
FALSE | 7.b | Internal User Activity Log => new menu | BE - WEB |  |  | @Kris
FALSE | 7.c | Periodic passwd /change enforce | DB- Trigger StoreProc + BE Admin disclaimer | System param/expiry | Status =securiritylocked | @Kris
FALSE | 7.d | Remove menu Suspended pocket | BE- WEB | setting/rolemenu |  | @Ary
FALSE | 7.e | Disable auto inactive , when blocking user | BE- WEB | Find “inActive” | Subscriber | @Martin | Ready for test | TESTED
FALSE | 7.f | Info upgrade Rejection | BE-WEB | subsc.upgrade.data | Js.
FALSE
FALSE | 8 | Server => IT
FALSE
FALSE | 9 | KYC- APU PPT |  | ?????? |  |  | Ready for test
FALSE |  | Enforce Mandatory field on AddOn Form

## Sheet 1
Table 1
| Item | Sample
Modify a page jsp/js
| Modify table and model | KYC info, and rejection Reason
| Modify query on Report and menu | Statement pending Union
Create/add menu
Alter API
Modify API query
Arsitektur teknis seluruh system
Scheduler